## VMware with Ansible
VMware Build Automation Task Lists
Tasks to be executed for Automation of Build and Post Install of Vmware
Task Number |  | Ansible Module For the Task | Module Descritption | Status | Module For ESXi/VCSA | Remarks
1 | Prepare Excel Sheet which will Provide Variables for Input to Playbooks |  |  | In Progress
ESXi Installation
2 | ESXi Installation | PXE Boot Installation |  | Completed
3 | ESXi IP, Subnet, Gateway & VLAN configuration | vmware_vmkernel_ip_config | Configure the VMkernel IP Address | Completed
4 | NTP Configuration | vmware_host_ntp | Manage NTP server configuration of an ESXi host | Completed
5 | DNS Configuration | vmware_dns_config | Manage VMware ESXi DNS Configuration | Completed
| Installation of AD for Infra | vmware_host_active_directory | Joins an ESXi host system to an Active Directory domain or leaves it
6 | Domain Server VM Creation (2 on each site) - Total 4 VMs | vmware_content_deploy_template | Deploy Virtual Machine from template stored in content library
7 | Setup AD - Domain Controller Installation (DNS and configuration) | ??
8 | DNS Configuration and 'A' record creation | vmware_dns_config | Manage VMware ESXi DNS Configuration
vCenter Appliance Installation & Configuration
9 | vCenter Appliance VM with embedded PSC Deployment (2) | Pending |  | Hardware Required to Test with Ansible with JSON input
10 | vCenter Appliance VM Confgiuration (2) | Pending |  | Hardware Required to Test with Ansible with JSON input
11 | HA/DRS Cluster Configuration | vmware_cluster_drs | Manage High Availability (HA) on VMware vSphere clusters | Require vcenter, playbook is ready
12 |  | vmware_cluster_ha | Manage Distributed Resource Scheduler (DRS) on VMware vSphere clusters | Require vcenter, playbook is ready
13 | vSwitch Configuration | vmware_vswitch | Manage a VMware Standard Switch to an ESXi host | Completed
14 |  | vmware_portgroup | Create a VMware portgroup + Port Group Policy | Completed |  | Only 1 Port Group Policy can be defined in one playbook
15 | dvSwitch Configuration | vmware_dvswitch | Create or remove a Distributed Switch | Achievable, playbook is ready
16 |  | vmware_dvs_portgroup | Create or remove a Distributed vSwitch | Achievable, playbook is ready
17 | Mgmt vSwitch to dvSwitch Migration | vmware_migrate_vmk |  | Achievable, playbook is ready
18 | vMotion PortGroup configuration | vmware_portgroup | Create a VMware portgroup | Completed
19 | vSAN PortGroup configuration | vmware_portgroup | Create a VMware portgroup | Completed
20 | Create DRS Rules | vmware_drs_group | Creates vm/host group in a given cluster | Require vcenter, playbook is ready
21 | vCenter and ESXi Server License Installation | vcenter_license | Manage VMware vCenter license keys | Achievable, playbook is ready
22 | Host Profile creation | No Module Found
23 | Apply Host Profile | No Module Found
| ???? | vmware_resource_pool | Add/remove resource pools to/from vCenter
vSAN Stretched Cluster
24 | Disable HA from HA/DRS Cluster
25 | Create vSAN Cluster (2 in nos. with 33 hosts) | vmware_cluster_vsan | Manages virtual storage area network (vSAN) configuration on VMware vSphere clusters
26 | Configure the vSAN Cluster | vmware_vsan_cluster | Configure VSAN clustering on an ESXi host
27 | Create Disk groups
28 | Create Stretched Cluster
29 | Create a fault domains for stretched cluster
30 | Download the Witness Host appliance
31 | Deploy Witness Host on Ruiel site (Total 2 Witness nodes)
32 | Configure the Witness Host Networking (Mgmt & vSAN Networking) & DNS
33 | Add the Witness host to vCenter on another cluster other than stretched cluster
34 | Configure the Witness Host
35 | Create vSAN Storage Policies for stretched cluster
36 | Enable HA from HA/DRS Cluster

## Manual Build Steps
ESXi Installation
ESXi Installation
ESXi IP, Subnet, Gateway & VLAN configuration
NTP Configuration
DNS Configuration
Installation of AD for Infra
Domain Server VM Creation (2 on each site) - Total 4 VMs
Setup AD - Domain Controller Installation (DNS and configuration)
DNS Configuration and 'A' record creation
vCenter Appliance Installation & Configuration
vCenter Appliance VM with embedded PSC Deployment (2)
vCenter Appliance VM Confgiuration (2)
HA/DRS Cluster Configuration
vSwitch Configuration
dvSwitch Configuration
Mgmt vSwitch to dvSwitch Migration
vMotion PortGroup configuration
vSAN PortGroup configuration
Create DRS Rules
vCenter and ESXi Server License Installation
Host Profile creation
Apply Host Profile
vSAN Stretched Cluster
Disable HA from HA/DRS Cluster
Create vSAN Cluster (2 in nos. with 33 hosts)
Configure the vSAN Cluster
Create Disk groups
Create Stretched Cluster
Create a fault domains for stretched cluster
Download the Witness Host appliance
Deploy Witness Host on Ruiel site (Total 2 Witness nodes)
Configure the Witness Host Networking (Mgmt & vSAN Networking) & DNS
Add the Witness host to vCenter on another cluster other than stretched cluster
Configure the Witness Host
Create vSAN Storage Policies for stretched cluster
Enable HA from HA/DRS Cluster